## Overview
FLOWRYD MVP PROJECT PLAN
Target: First Revenue Feb 21, 2026 ¦ Discover 1.0 + Private Canvas 1.1
TIMELINE SUMMARY
Week | Dates | Milestone | Owner
Week 1 | Feb 3-7 | NODE LIVE + API DEPLOYED | IEU + Will
Week 2 | Feb 10-14 | DISCOVER 1.0 LIVE | Will
Week 3 | Feb 17-21 | FIRST REVENUE (Texture subscribes) | Liz + Will
Week 4 | Feb 24-28 | CANVAS 1.1 + FIRST FLOW | All

## LIZ - Must Dos
LIZ - MUST DO CHECKLIST
✓ | Week | Task | Due | Status | Notes
☐ | W0 | Get Chata subscription DAML code | Feb 3 | PENDING | Verbal agreement exists
☐ | W0 | Confirm Texture Capital as design partner #1 | Feb 3 | PENDING | Deck already shown
☐ | W0 | Review IEU demo video with Will | Feb 3 | PENDING | Link in email
☐ | W1 | Prepare 3-5 'Behind the Flows' content pieces | Feb 7 | NOT STARTED | Franklin, DTCC, State Street
☐ | W1 | Curate party logos for network grid | Feb 7 | NOT STARTED | Top 20 Canton participants
☐ | W2 | Test Discover 1.0 before launch | Feb 14 | NOT STARTED | Click capture working?
☐ | W2 | Onboard Texture Capital (schedule call) | Feb 14 | NOT STARTED | Demo subscription flow
☐ | W3 | TEXTURE SUBSCRIBES - FIRST REVENUE | Feb 21 | MILESTONE | $100 CC payment
☐ | W3 | Identify design partner #2 and #3 | Feb 21 | NOT STARTED | C7 Trust? Memora?
☐ | W4 | Support Texture first flow creation | Feb 28 | NOT STARTED | DAT Tokenization
☐ | W4 | Collect feedback, plan 1.2 iteration | Feb 28 | NOT STARTED | What worked/didn't

## WILL - Must Dos
WILL - MUST DO CHECKLIST
✓ | Week | Task | Due | Status | Notes
☐ | W0 | Review IEU demo video | Feb 3 | PENDING | Link shared by Anastasiia
☐ | W0 | Prepare API bridge for node connection | Feb 3 | PENDING | Already built Nov 2025
☐ | W0 | Review HTML prototypes + Figma handoffs | Feb 3 | PENDING | Discover + Canvas
☐ | W1 | Receive node credentials from IEU | Feb 5 | WAITING | Anastasiia to send
☐ | W1 | Test API bridge against live Canton node | Feb 6 | NOT STARTED | Holdings + Validators
☐ | W1 | DEPLOY API BRIDGE TO PRODUCTION | Feb 7 | MILESTONE | Real data flowing
☐ | W1 | Start Figma: participant-logo component | Feb 7 | NOT STARTED | Core click capture component
☐ | W2 | Convert Discover HTML → React | Feb 12 | NOT STARTED | Use prototype as reference
☐ | W2 | Build click capture API endpoints | Feb 12 | NOT STARTED | On-chain interest signals
☐ | W2 | Integrate Chata subscription code | Feb 13 | NOT STARTED | CC payment flow
☐ | W2 | DISCOVER 1.0 DEPLOYED | Feb 14 | MILESTONE | Live network data
☐ | W3 | Convert Canvas HTML → React | Feb 19 | NOT STARTED | Private flow builder
☐ | W3 | Build flow canvas components | Feb 19 | NOT STARTED | role-node, offer-card
☐ | W3 | Integrate DAML offer/commit | Feb 20 | NOT STARTED | Flowryd library
☐ | W3 | PRIVATE CANVAS 1.1 DEPLOYED | Feb 21 | MILESTONE | Texture can create flows
☐ | W4 | Support Texture first flow | Feb 28 | NOT STARTED | Debug issues
☐ | W4 | Iterate based on feedback | Feb 28 | NOT STARTED | Quick fixes

## IEU - Must Dos
IEU - MUST DO CHECKLIST
✓ | Week | Task | Due | Status | Notes
☐ | W0 | Complete Flowryd validator deployment | Feb 3-5 | IN PROGRESS | Per Anastasiia email
☐ | W1 | Send node credentials to Will | Feb 5 | PENDING | Unblocks API bridge
☐ | W1 | Share demo video access | Feb 3 | DONE | Link shared Jan 30
☐ | W1 | Review Chata subscription code (if needed) | Feb 7 | NOT STARTED | Validate patterns
☐ | W2 | Review Flowryd DAML library | Feb 14 | NOT STARTED | 2,244 LOC
☐ | W2 | Deploy subscription contract to TestNet | Feb 14 | NOT STARTED | CC payment flow
☐ | W3 | Deploy offer/commit contracts | Feb 21 | NOT STARTED | From Flowryd library
☐ | W3 | Support Texture pilot onboarding | Feb 21 | NOT STARTED | First real flow
☐ | W4 | Debug any Canton issues | Feb 28 | NOT STARTED | As needed

## Blockers + Deps
BLOCKERS & DEPENDENCIES
✓ | Blocker | Owner | Blocks | Status | Resolution
☐ | Canton node access | IEU | Will's API bridge | IN PROGRESS | ETA Feb 3-5
☐ | Chata subscription code | Liz | CC payment flow | PENDING | Get this week
☐ | Texture confirmation | Liz | First revenue | VERBAL | Confirm this week
☐ | Demo video review | Will | Understanding platform | READY | Link shared

## Milestones
KEY MILESTONES
✓ | Date | Milestone | Success Criteria | Owner
☐ | Feb 5 | Node credentials received | Will can connect to Canton | IEU
☐ | Feb 7 | API BRIDGE LIVE | Real data flowing to frontend | Will
☐ | Feb 14 | DISCOVER 1.0 LIVE | Network grid + click capture working | Will
☐ | Feb 21 | FIRST REVENUE | Texture pays $100 CC | Liz
☐ | Feb 21 | CANVAS 1.1 LIVE | Texture can create flows | Will
☐ | Feb 28 | FIRST FLOW CREATED | DAT Tokenization flow on-chain | Texture
☐ | Feb 28 | FIRST OFFER SENT | Offer contract created | Texture